## Master Roadmap
PermitPal — Product Build Roadmap
Short-Term Rental Compliance SaaS · US + EU + AU · 24-Month Plan
| Phase | Domain | Feature / Task | Priority | M1-2 | M3-4 | M5-6 | M7-8 | M9-10 | M11-12 | M13-18 | M19-24 | Owner | Notes
| 0·Foundation | Infrastructure | Monorepo .NET 8 WebAPI + React + Vite | P0 | ✓ | [7 empty] | CTO | healthdesk.sln pattern
|  | Infrastructure | MySQL 8 schema — 12 domain tables | P0 | ✓ | [7 empty] | CTO | permitpal_schema.sql
|  | Infrastructure | JWT auth + TenantMiddleware.cs | P0 | ✓ | [7 empty] | CTO | organisation_id isolation
|  | Infrastructure | Cloudflare R2 — permit document storage | P0 | ✓ | [7 empty] | CTO | PDFs, certificates
|  | Infrastructure | CI/CD GitHub Actions + Railway deploy | P0 | ✓ | [7 empty] | CTO | PR preview envs
|  | Infrastructure | Redis + Hangfire background jobs | P0 | ✓ | [7 empty] | CTO | alert jobs, reg monitoring
|  | Payments | Stripe subscription billing | P0 | ✓ | ✓ | [6 empty] | Dev | Solo/Host/Operator plans
| 1·MVP | Property | Property create — address, country, type | P0 |  | ✓ | ✓ | [5 empty] | Dev | Geocode → jurisdiction lookup
|  | Property | Jurisdiction resolver — map address to rules | P0 |  | ✓ | ✓ | [5 empty] | Dev | Core engine — postcode → ruleset
|  | Property | Compliance profile page per property | P0 |  | ✓ | ✓ | [5 empty] | Dev | What permits needed, current status
|  | Permits | Permit CRUD — number, issue/expiry, authority | P0 |  | ✓ | ✓ | [5 empty] | Dev | Link to jurisdiction
|  | Permits | Document vault — upload/store/preview permit PDFs | P0 |  |  | ✓ | ✓ |  |  |  |  | Dev | R2 storage, expiry tagging
|  | Permits | 90/30/7 day renewal alerts — email + SMS | P0 |  |  | ✓ | ✓ |  |  |  |  | Dev | Hangfire recurring job
|  | Permits | One-click renewal link per jurisdiction | P1 |  |  | ✓ | ✓ |  |  |  |  | Dev | 200 portal URLs seeded
|  | Night Cap | iCal sync — import Airbnb/VRBO calendar | P0 |  |  | ✓ | ✓ |  |  |  |  | Dev | Night counter from bookings
|  | Night Cap | Night cap tracker per property | P0 |  |  | ✓ | ✓ |  |  |  |  | Dev | Alert at 80%/90%/100%
|  | Night Cap | Calendar year reset logic | P0 |  |  | ✓ | ✓ |  |  |  |  | Dev | Jan 1 reset, Byron Shire June
|  | Dashboard | Compliance score 0–100 per property | P0 |  |  |  | ✓ |  |  |  |  | Dev | Red/Amber/Green status
|  | Dashboard | Multi-property portfolio view | P0 |  |  |  | ✓ |  |  |  |  | Dev | Host plan — up to 5 props
|  | Alerts | Regulatory change alert engine | P1 |  |  |  | ✓ | ✓ |  |  |  | Dev | Monitor rule changes, notify users
| 2·EU Compliance | EU Reg | EU Reg 2024/1028 compliance wizard | P0 |  |  |  |  | ✓ | ✓ |  |  | Dev | Step-by-step per member state
|  | EU Reg | France — Déclaratrion / Déclaraloc guide | P0 |  |  |  |  | ✓ | ✓ |  |  | Dev | 120-night cap, Loi Le Meur
|  | EU Reg | Spain — NRU registration guide | P0 |  |  |  |  | ✓ | ✓ |  |  | Dev | Link to Registro de viajeros
|  | EU Reg | Netherlands — BRP registration guide | P0 |  |  |  |  | ✓ | ✓ |  |  | Dev | Amsterdam 30/15 night cap
|  | EU Reg | Germany — Zweckentfremdung guide | P0 | [5 empty] | ✓ |  |  | Dev | City by city — Berlin, Munich
|  | EU Reg | Portugal — RNAL registration guide | P1 | [5 empty] | ✓ |  |  | Dev | Registo Nacional AL
|  | EU Reg | Italy — CIR code registration guide | P1 | [5 empty] | ✓ |  |  | Dev | Codice Identificativo Regionale
|  | EU Reg | Registration number validator | P0 |  |  |  |  | ✓ | ✓ |  |  | Dev | API check against national registries
|  | EU Reg | Platform data reconciliation report | P1 | [5 empty] | ✓ |  |  | Dev | What EU platforms reported to authorities
|  | EU Reg | EU night-cap monitoring — city by city | P0 |  |  |  |  | ✓ | ✓ |  |  | Dev | Paris 120, Amsterdam 30, Lyon 120
| 3·AU Compliance | NSW | NSW STRA register guide + fee tracker | P0 |  |  |  |  | ✓ | ✓ |  |  | Dev | $65 new, $25 renewal, PID display
|  | NSW | 180-night cap tracker — Greater Sydney | P0 |  |  |  |  | ✓ | ✓ |  |  | Dev | Byron Shire 60-night variant
|  | Victoria | Victoria 7.5% Short Stay Levy calculator | P0 | [5 empty] | ✓ |  |  | Dev | Quarterly SRO report for direct bookings
|  | Victoria | Strata/OC ban tracker | P1 | [5 empty] | ✓ |  |  | Dev | Monitor Land Use Victoria register
|  | WA | WA STRA registration guide | P0 |  |  |  |  | ✓ | ✓ |  |  | Dev | $250 new/$100 renewal, 90-night Perth
|  | Queensland | Brisbane permit guide (mid-2026 laws) | P0 | [5 empty] | ✓ |  |  | Dev | Complaint log, 60-min timer
|  | Safety | Fire safety compliance checklist AU | P0 | [5 empty] | ✓ |  |  | Dev | AS 3786, extinguisher, evac diagram
|  | Tax | ATO income report export | P1 | [6 empty] | ✓ |  | Dev | myTax-ready, GST flag
| 4·US + Growth | US Rules | City rules DB — top 10 US cities | P0 |  |  |  |  | ✓ | ✓ |  |  | Dev | NYC, SF, Austin, Nashville, Miami…
|  | US Rules | City rules DB — 500 cities | P1 | [6 empty] | ✓ |  | Dev | Regulatory data team or API
|  | US Rules | TOT / occupancy tax rate tracker | P0 | [5 empty] | ✓ |  |  | Dev | City + county rates, self-remit flag
|  | US Rules | Zoning check — STR permitted in zone? | P1 | [5 empty] | ✓ |  |  | Dev | GIS zoning API integration
|  | US Rules | License display checker | P1 | [6 empty] | ✓ |  | Dev | Scan Airbnb listing for permit # in desc
|  | Integrations | Hostaway integration — booking sync | P1 | [6 empty] | ✓ |  | Dev | Auto night-cap counting
|  | Integrations | Hospitable integration | P1 | [6 empty] | ✓ |  | Dev | App store listing
|  | Integrations | Guesty integration | P2 | [6 empty] | ✓ |  | Dev | Enterprise PMS
|  | Reporting | White-label compliance report PDF | P1 | [6 empty] | ✓ |  | Dev | Property manager client reports
|  | Reporting | Operator portfolio dashboard | P0 | [6 empty] | ✓ |  | Dev | 20+ properties, team seats
| 5·Scale | Content | SEO city guides — 50 cities published | P0 |  |  |  |  | ✓ | ✓ | ✓ |  | Mktg | 'Austin STR permit 2025' etc
|  | Content | Regulatory alert newsletter | P1 | [5 empty] | ✓ | ✓ |  | Mktg | Weekly email to all users
|  | Expansion | UK STR licensing (Scotland, England, Wales) | P2 | [7 empty] | ✓ | Dev | Post-Brexit own framework
|  | Expansion | Canada STR compliance (Toronto, Vancouver) | P2 | [7 empty] | ✓ | Dev | Phase 6
|  | Expansion | New Zealand STR compliance | P2 | [7 empty] | ✓ | Dev | Phase 6

## Tech Stack
PermitPal — Technology Stack (.NET 8 + MySQL + React)
Same pattern as HealthDesk — consistent across both products
Layer | Choice | Why | Alt | Cost | Notes
Backend | .NET 8 Web API (C#) | Fast, typed, great for complex domain logic | FastAPI | OSS | Same as HealthDesk — one stack to learn
Frontend | React 18 + Vite | SPA — dashboard, map views, calendar | Next.js | OSS | Vite faster for dev, React Query for data
UI | Tailwind + shadcn/ui | Rapid UI, consistent with HealthDesk | MUI | OSS | Same design system across both products
Database | MySQL 8.0 | Structured compliance rules, JSON for rule sets | PostgreSQL | OSS | PlanetScale or AWS RDS — same as HealthDesk
ORM | EF Core + Pomelo MySQL | Type-safe queries, migrations | Dapper | OSS | Same pattern as HealthDesk.Api
Auth | JWT + ASP.NET Identity | Stateless, multi-tenant via TenantMiddleware | Auth0 | OSS | MFA via TOTP — Otp.NET NuGet
Background Jobs | Hangfire + Redis | Permit renewal alerts, nightly rule scraper | Quartz.NET | OSS+$20/mo | RecurringJob.AddOrUpdate() for alert cadence
File Storage | Cloudflare R2 | Permit PDFs, safety certs — no egress fees | S3 | ~$0.015/GB | AWSSDK.S3 NuGet, pre-signed URLs
Payments | Stripe | Subscription billing — Solo/Host/Operator | Paddle | 2.9%+30c | Stripe Customer Portal for self-serve upgrades
SMS | Twilio | Permit renewal SMS alerts | MessageBird | ~$0.075/SMS | US + EU + AU numbers
Email | Resend | Regulatory change alerts, renewal reminders | SendGrid | Free→$20/mo | React Email templates
Geocoding | Google Maps API | Address → lat/lng → jurisdiction lookup | Mapbox | $0.005/req | GeocodeAddress() → PostcodeToJurisdiction()
Mapping | Leaflet.js | Property map view, zoning overlay | Google Maps | OSS | Show STR zones on property location map
Calendar Sync | iCalendar (.ics) | Import Airbnb/VRBO/Booking calendars | OAuth API | OSS | Parse VEVENT → count DTSTART nights
AI Alerts | Anthropic Claude API | Summarise regulatory changes into plain English | OpenAI | $3/M tokens | claude-haiku — weekly rule monitoring summaries
PDF | QuestPDF | Compliance report PDF, permit summaries | iTextSharp | OSS | Same as HealthDesk invoice PDFs
Monitoring | Sentry + PostHog | Error tracking + product analytics | Datadog | Free tiers | PostHog EU instance for GDPR
Deployment | Railway.app | Simple PaaS, MySQL add-on, auto-deploys | Render | ~$20/mo start | Same infra as HealthDesk
CI/CD | GitHub Actions | Build + test + deploy on every PR | CircleCI | Free tier | Same workflow as HealthDesk
Secrets | Doppler | Dev → staging → prod secret promotion | AWS Secrets | $10/mo | Same setup as HealthDesk

## Milestones
PermitPal — Key Milestones & Success Metrics
24-Month journey from zero to $1M ARR
Month | Milestone | Success Metric | MRR Target | Users | Phase Gate | Key Risk
Month 2 | Schema + auth + property compliance profile | Host can enter address, see their permit requirements | $0 | 0 | Tech foundation done | Jurisdiction resolver returns wrong rules
Month 3 | Night-cap counter + iCal sync live | First host syncs Airbnb calendar, nights counted accurately | $0 | 20 beta | Beta hosts validate accuracy | iCal format differs per platform
Month 4 | EU Reg 2024/1028 wizard live | 50 EU hosts register through PermitPal wizard | $0 | 50 beta | EU registration guide correct per country | National portals change their UX
Month 5 | First paid customers — Solo plan $19/mo | 100 paying hosts — EU urgency drives signups | $1,900 | 100 | Revenue > $0 | Price too high — offer 50% beta discount
Month 6 | AU compliance live — NSW + VIC + WA | AU hosts tracking night caps and levy obligations | $4,500 | 200 | AU NPS > 7 | State rules more complex than expected
Month 8 | US top 10 cities live | US hosts tracking TOT and permit renewals | $9,000 | 400 | Zero incorrect city rules reported | City rules change — monitoring needed
Month 10 | PMS integrations — Hospitable + Hostaway | 30% of bookings synced automatically vs manual iCal | $18,000 | 700 | PMS app store published | API rate limits, OAuth complexity
Month 12 | Operator plan + property manager channel | 50 operators (20+ props each) → 1,000 properties managed | $28,000 | 1,200 | Operator churn < 3%/mo | Property managers want white-label
Month 15 | $60K MRR — 2,000 hosts | White-label reports + team seats driving upsell | $60,000 | 2,000 | NPS > 8 across all markets | Competitor launches similar product
Month 18 | SEO flywheel — 100K organic visitors/mo | 50+ city guides ranking on page 1 for STR permit queries | $80,000 | 2,800 | CAC < $30 from organic | Google algorithm change hits rankings
Month 22 | $1M ARR milestone | ~4,200 paying hosts + operators | $83,000 | 4,200 | Series A readiness; < 3% monthly churn | Platform (Airbnb) builds native compliance tool
Month 24 | Canada + UK expansion | 200 UK/CA hosts on waitlist converted to paid | $95,000 | 4,800 | UK Scottish licensing covered | Post-Brexit UK rules require separate DB

## Sprint Plan M1-M6
PermitPal — Detailed Sprint Plan (Months 1–6, 2-week sprints)
12 sprints from zero to 200 paying hosts with AU + EU compliance live
Sprint | Month | Goal | Stories / Tasks | Acceptance Criteria | Points | Owner
S1 | M1 | Repo + DB + Auth | dotnet new sln; MySQL schema 12 tables; JWT auth; org + user CRUD; TenantMiddleware | Dev can register org, log in, RLS blocks cross-org queries | 21 | CTO
S2 | M1 | Property + jurisdiction resolver | Property CRUD; geocode address → postcode; PostcodeToJurisdiction() returns ruleset JSON | Enter Sydney address → returns: STRA required, 180-night cap, $65 fee | 22 | Dev
S3 | M2 | Permit tracker | Permit CRUD — number, issue/expiry, authority, document upload to R2; Hangfire renewal jobs | Permit created; 90d alert fires correctly in test; document stores to R2 | 20 | Dev
S4 | M2 | Night-cap counter + iCal | Parse iCal .ics from Airbnb URL; VEVENT → count DTSTART nights per property; alert at 80%/90% | iCal imports correctly; Sydney property shows correct nights used of 180 | 22 | Dev
S5 | M3 | Dashboard + compliance score | Property list with score 0-100; Red/Amber/Green; portfolio multi-property view; Stripe Solo plan | Score calculates correctly; Stripe billing activates after trial | 19 | Dev
S6 | M3 | EU Reg 2024/1028 wizard — France + Spain | Step-by-step France Déclaratrion guide; Spain NRU guide; reg number store + validator | French host completes wizard in < 10 min; reg number validated format | 21 | Dev
S7 | M4 | EU wizard — NL + DE + PT + IT | Netherlands BRP guide; Germany Zweckentfremdung; Portugal RNAL; Italy CIR; EU night-cap data | 4 more EU countries complete; Amsterdam 30-night cap tracked correctly | 20 | Dev
S8 | M4 | AU — NSW + WA | NSW STRA guide ($65/$25 fees); WA guide ($250/$100); Byron Shire 60-night variant; fire safety checklist | NSW host registers through portal link; WA PID stored and displayed | 21 | Dev
S9 | M5 | AU — Victoria levy + Brisbane | Victoria 7.5% levy calculator + SRO quarterly report; Brisbane permit guide + complaint log + timer | Levy calculated correctly on direct booking; Brisbane 60-min alert fires | 19 | Dev
S10 | M5 | US — top 10 cities | City rules DB: NYC, SF, Austin, Nashville, Miami, Denver, Seattle, Chicago, LA, Honolulu; TOT tracker | 10 city rulesets correct; TOT rate returned for each city | 22 | Dev
S11 | M6 | Regulatory change alerts | Claude API monitors rule changes; summarises change in plain English; pushes to affected users within 24h | Test rule change triggers correct user notifications | 18 | Dev+CTO
S12 | M6 | Beta feedback + first 200 paid hosts | Bug fixes from beta; onboarding UX; help docs; referral program (1 free month per referral) | 200 paying hosts by end M6; NPS ≥ 7; top bugs resolved | — | All

## API Endpoints
PermitPal — REST API Endpoint Reference
All endpoints for .NET 8 Web API controllers
Method | Endpoint | Description | Auth | Phase | Market | Notes
POST | /auth/register | Register org + owner account | Public | P1 | All | Creates org + user
POST | /auth/login | Login — return JWT + refresh | Public | P1 | All
POST | /auth/refresh | Refresh access token | JWT | P1 | All
POST | /auth/mfa/setup | TOTP MFA setup | JWT | P1 | All | Returns QR code
GET | /orgs/me | Get current org + subscription | JWT | P1 | All
PATCH | /orgs/me | Update org settings | JWT+Admin | P1 | All
GET | /properties | List all properties for org | JWT | P1 | All | ?page=1&limit=20
POST | /properties | Create property | JWT | P1 | All | Triggers jurisdiction resolver
GET | /properties/:id | Get property + compliance profile | JWT | P1 | All | Returns ruleset, permits, score
PATCH | /properties/:id | Update property details | JWT | P1 | All
DELETE | /properties/:id | Archive property | JWT | P1 | All | Soft delete
GET | /properties/:id/score | Get compliance score 0–100 | JWT | P1 | All | Red/Amber/Green + breakdown
GET | /jurisdictions/lookup | Resolve postcode → jurisdiction ruleset | JWT | P1 | All | ?postcode=2000&country=AU
GET | /jurisdictions/:id | Get full ruleset for jurisdiction | JWT | P1 | All | Night cap, permit types, fees, taxes
GET | /jurisdictions/:id/permits | List required permit types | JWT | P1 | All
GET | /permits | List permits for org | JWT | P1 | All | ?property_id=&expiring_days=30
POST | /permits | Create permit record | JWT | P1 | All
GET | /permits/:id | Get permit detail + document | JWT | P1 | All
PATCH | /permits/:id | Update permit / renew | JWT | P1 | All | Resets expiry date
DELETE | /permits/:id | Delete permit | JWT | P1 | All
POST | /permits/:id/document | Upload permit PDF to R2 | JWT | P1 | All | Multipart form
GET | /permits/:id/renewal-link | Get renewal portal URL | JWT | P1 | All | Returns jurisdiction portal URL
GET | /night-caps | List night-cap records for org | JWT | P1 | All
POST | /night-caps/:id/sync | Trigger iCal sync for property | JWT | P1 | All | Fetches calendar, counts nights
GET | /night-caps/:id/status | Current nights used vs cap | JWT | P1 | All | Returns pct used, alert threshold
POST | /night-caps/:id/ical | Set iCal URL for property | JWT | P1 | All | Airbnb/VRBO/Booking ical URLs
POST | /eu/register/france | Start France Déclaratrion wizard | JWT | P2 | EU | Returns step-by-step guide
POST | /eu/register/spain | Start Spain NRU wizard | JWT | P2 | EU
POST | /eu/register/netherlands | Start Netherlands BRP wizard | JWT | P2 | EU
POST | /eu/register/germany | Start Germany Zweckentfremdung wizard | JWT | P2 | EU
POST | /eu/register/portugal | Start Portugal RNAL wizard | JWT | P2 | EU
POST | /eu/register/italy | Start Italy CIR wizard | JWT | P2 | EU
GET | /eu/validate-registration/:country/:number | Validate reg number against national registry | JWT | P2 | EU | Returns valid/invalid/expired
GET | /eu/night-caps/:city | Get current EU city night cap | JWT | P2 | EU | Paris, Amsterdam, Lyon, Barcelona
GET | /au/nsw/register | NSW STRA registration guide | JWT | P3 | AU | Returns steps, fees, portal link
GET | /au/vic/levy-calculator | Victoria levy calculation | JWT | P3 | AU | ?booking_value_cents=50000
POST | /au/vic/levy-report | Generate SRO quarterly levy report | JWT | P3 | AU | Returns CSV for SRO lodgement
GET | /au/wa/register | WA STRA registration guide | JWT | P3 | AU | $250 new/$100 renewal
POST | /au/brisbane/complaint-log | Log a neighbour complaint | JWT | P3 | AU | Starts 60-min response countdown
GET | /au/fire-safety/:state | Fire safety checklist for AU state | JWT | P3 | AU | AS 3786 requirements by state
GET | /us/cities | List supported US cities with rules | JWT | P4 | US | ?state=TX&page=1
GET | /us/cities/:city_slug | Full STR ruleset for US city | JWT | P4 | US | Permit type, night cap, TOT rate
GET | /us/zoning | Check if STR permitted at address | JWT | P4 | US | ?address=123+Main+St+Austin+TX
GET | /us/tot-rates/:city_slug | Get TOT rate for city | JWT | P4 | US | State + county + city combined
GET | /us/listing-check | Scan Airbnb listing for permit number | JWT | P4 | US | ?listing_url=airbnb.com/rooms/123
GET | /reports/compliance | Org compliance summary report | JWT | P4 | All | PDF download
GET | /reports/portfolio | Multi-property portfolio report | JWT+Operator | P4 | All
GET | /reports/expiring | Permits expiring in next 90 days | JWT | P1 | All | ?days=30
GET | /regulatory-alerts | List regulatory change alerts for org | JWT | P1 | All | Paginated
POST | /regulatory-alerts/subscribe | Subscribe to alerts for a jurisdiction | JWT | P1 | All
GET | /documents | List all uploaded documents | JWT | P1 | All | ?property_id=&type=permit
POST | /documents | Upload document to R2 | JWT | P1 | All | Multipart
GET | /documents/:id/download | Get pre-signed download URL | JWT | P1 | All | Expires 15 min
POST | /webhooks/stripe | Stripe subscription webhook | Stripe-Sig | P1 | All
POST | /webhooks/twilio | Twilio SMS delivery receipt | Twilio-Sig | P1 | All

## Team & Costs
PermitPal — Team Structure & Monthly Cost Model
Lean team — regulatory data is the key investment
TEAM STRUCTURE
Role | When | Monthly Cost (USD) | Key Responsibility | Skills | Notes
Founder/CTO | Day 1 | $0 | Architecture; jurisdiction resolver; MySQL; Hangfire | C#; MySQL; React | Must understand compliance domain deeply
Full-stack Dev #1 | Month 1 | $6,000–$10,000 | Backend + frontend features | C#; React; EF Core | Can be offshore — async-first
Regulatory Data Analyst | Month 2 | $3,000–$5,000 | Map city/state/country rules; keep DB current | Research; spreadsheets; basic SQL | Most important non-tech hire — makes the product correct
Part-time Designer | Month 1 | $2,000–$3,000 | Dashboard UX; compliance score visuals; Figma | Figma; Tailwind; product design | Compliance tools must feel trustworthy — design matters
Full-stack Dev #2 | Month 4 | $6,000–$10,000 | EU wizard; iCal sync; PMS integrations | C#; React; OAuth | Doubles velocity for P2/P3 features
Content / SEO Writer | Month 5 | $2,000–$4,000 | City guide articles; regulatory alerts newsletter | SEO writing; STR knowledge; WordPress | 50 city guides = primary acquisition channel
Customer Success | Month 6 | $3,000–$5,000 | Onboarding; support; NPS tracking | Empathy; STR domain knowledge | Ideally ex-Airbnb host or property manager
Sales / Growth | Month 9 | $3,000–$6,000 + commission | PMS partnerships; operator outreach | B2B SaaS; marketplace partnerships | Commission on Operator plan activations
MONTHLY INFRASTRUCTURE COSTS
Service | Provider | Phase 1 Cost | Phase 3 Cost | Phase 5 Cost | Notes
MySQL (PlanetScale) | PlanetScale | $0/mo | $39/mo | $199/mo | Free tier generous; scales with rows
App hosting | Railway | $20/mo | $80/mo | $300/mo | API + worker + React static
Redis (Upstash) | Upstash | $0/mo | $20/mo | $60/mo | Hangfire storage + alert caching
File storage (R2) | Cloudflare R2 | $5/mo | $15/mo | $50/mo | Permit PDFs, safety docs
SMS (Twilio) | Twilio | $30/mo | $100/mo | $400/mo | Renewal alerts — SMS volume
Email (Resend) | Resend | $0/mo | $20/mo | $80/mo | Regulatory alerts, renewal emails
Geocoding | Google Maps API | $10/mo | $40/mo | $200/mo | $5/1000 geocoding requests
AI alerts (Claude) | Anthropic | $10/mo | $40/mo | $150/mo | Haiku for rule change summaries
Regulatory data | Manual/team | $0/mo | $3,000/mo | $5,000/mo | Analyst keeping DB current — biggest cost
Monitoring | Sentry + PostHog | $0/mo | $26/mo | $80/mo | Free tiers generous
Domain + SSL | Cloudflare | $15/yr | $15/yr | $15/yr | Proxy + DDoS free
TOTAL INFRA | — | ~$80/mo | ~$350/mo + analyst | ~$1,500/mo + analyst | Regulatory team is the real cost at scale